## List of Labs
S. N. | Lab Title | Chapter mapped | Hint
1 | Create and explore account in any claoud basedProject management platform. | 1
2 | Calculate NPV of the given cashflow | 2
3 | Calculate NFV of the given cashflow | 2
4 | Calculate NAV of the given cashflow | 2
5 | Defining and adjusting work time | 3
6 | Ecaluating Critical Task, Slack and Late Tasks | 3 | LAB 7
7 | Generating Report in MS project | 3 | LAB 8
8 | Short out top 5 risks out of 10 given risks on the basis of risk exposure | 4
9 | Evaluate given risk in probability-impact matrix and finalize the risks above tolerance line. Assume tolerance line as per your projects nature. | 4
10 | Demonstrate resource allocation in MS Project | 5 | LAB 4
11 | Create Gnatt chart for the given schedule | 6 | LAB 2
12 | Create an approprate bar chart or pie-chart for given data | 6
13 | Create a ball chart from the given data | 6
14 | Tracking Progress of the tasks in the project | 6 | Lab 6

## Cah flow
Year | Cash Flow
0 | -10000
1 | 2000
2 | 3000
3 | 4000
4 | 5000
NPV | 717.8471
NFV
NAV

## Ball Chart
Project | Investment Cost (Rs. lakh) | Expected Return (%) | Risk Level (Score 1-10)
A | 50 | 12 | 4
B | 80 | 15 | 7
C | 40 | 10 | 3
D | 100 | 20 | 8
E | 60 | 13 | 5

## Bar Chart
Activity | Time Spent (Hours)
1. Requirements Gathering | 40
2. Stakeholder Meetings | 25
3. Feasibility Analysis | 15
4. Project Planning | 30
5. Risk Analysis | 10
6. Resource Allocation | 20
7. UI/UX Design | 35
8. Backend Development | 80
9. Frontend Development | 70
10. API Integration | 25
11. Database Design | 20
12. Testing (Unit) | 30
13. Testing (Integration) | 25
14. Testing (UAT) | 15
15. Bug Fixing | 20
16. Documentation | 15
17. Version Control Management | 10
18. Code Review | 10
19. Deployment | 15
20. Post-project Evaluation | 10

## Pie Chart
Project Phase | Time Spent (Hours)
Planning | 60
Design | 40
Development | 100
Testing | 50
Deployment | 30

## RiskExposure
S. N. | Risk | Probability | Impact (NPR)
1 | Scope creep | 0.28 | 35000
2 | Vendor non-responsiveness | 0.22 | 50000
3 | Delayed approvals from stakeholders | 0.05 | 80000
4 | Lack of skilled resources | 0.12 | 40000
5 | Technical debt | 0.18 | 30000
6 | Dependencies on third-party tools | 0.1 | 100000
7 | Lack of training for end-users | 0.2 | 15000
8 | Poor documentation | 0.25 | 25000

## Prob-impact
S. N. | Risk | Probability | Impact (NPR) | Code
1 | Delay in procurement | High | Critical | R1
2 | Budget overrun in development phase | Moderate | Minor | R2
3 | Non-compliance with regulations | Low | Low | R3
4 | Insufficient testing resources | Normal | Major | R4
5 | Communication gaps | Normal | Low | R5
6 | Supplier delays | High | Low | R6
7 | Resource unavailability | Low | Critical | R7
8 | Lack of contingency plans | High | Major | R8

## Sheet1
Critical |  |  |  | R1
Major
Minor
Low
| Normal | Low | Moderate | High
Probability
Impact