## Sheet1
S. N. | Risk | Probability | Impact (NPR) | Risk Exposure
2 | Vendor non-responsiveness | 0.22 | 50000 | 11000
6 | Dependencies on third-party tools | 0.1 | 100000 | 10000
1 | Scope creep | 0.28 | 35000 | 9800
8 | Poor documentation | 0.25 | 25000 | 6250
5 | Technical debt | 0.18 | 30000 | 5400
4 | Lack of skilled resources | 0.12 | 40000 | 4800
3 | Delayed approvals from stakeholders | 0.05 | 80000 | 4000
7 | Lack of training for end-users | 0.2 | 15000 | 3000