## Sheet1
S. N. | Risk | Probability | Impact (NPR) | Code
1 | Delay in procurement | High | Critical | R1
2 | Budget overrun in development phase | Moderate | Minor | R2
3 | Non-compliance with regulations | Low | Low | R3
4 | Insufficient testing resources | Normal | Major | R4
5 | Communication gaps | Normal | Low | R5
6 | Supplier delays | High | Low | R6
7 | Resource unavailability | Low | Critical | R7
8 | Lack of contingency plans | High | Major | R8
[5 empty] | Critical |  | R7 |  | R1
[5 empty] | Major | R4 |  |  | R8
[5 empty] | Minor |  |  | R2
[5 empty] | Low | R5 | R3 |  | R6
[6 empty] | Normal | Low | Moderate | High
IMPACT
PROBABILITY